DUTA INTEGRA SOLUTIONS

Startup Checklist — Status Update

Original checklist: March 2026  |  Status reviewed: 24 August 2026

Where things actually stand

This checklist was written as a generic first-90-days template. Five months in, Duta Integra is well past most of Phase 1–3: SSM and the bank account are done, three active client relationships exist (Lapango, Eastelpro, AGMX), and the current priority isn't finding first clients — it's converting the existing ones into retainers. The table below re-marks every original item against where things stand now, so this can serve as a living tracker instead of a stale document.

Legend:  ✅ Done   🔄 In Progress   ⏳ Pending   ❓ Confirm (status not in our records — check with you)   ◻ Not Started   ⏭ Deferred (not yet applicable)

📋 PHASE 1 — Legal & Compliance Setup

| Task | Priority | Status | Notes |
| --- | --- | --- | --- |
| Confirm SSM registration is complete and certificate received | ⚡ Urgent | ✅ Done | Registered. |
| Open a dedicated business bank account | ⚡ Urgent | ✅ Done | Confirmed in place. |
| Register for tax number with LHDN | ⚡ Urgent | ⏳ Pending | Outstanding admin item — still open. |
| Assess SST registration requirement (revenue > RM500k) | High | ⏭ Deferred | Not yet applicable — revisit once MRR/revenue approaches threshold. |
| Draft standard service agreement and NDA templates | High | 🔄 In Progress | Combined Service Agreement + NDA template drafted; needs Malaysian legal review before first use. |
| Ensure PDPA compliance policy is in place | High | 🔄 In Progress | PDPA Compliance Policy drafted; needs legal review — credibility requirement before pitching PDPA services or grants. |
| Register on ePerolehan (MyProcurement) for gov contracts | Medium | ◻ Not Started | Not started — low priority vs. current SME/retainer focus. |

🎨 PHASE 2 — Branding & Marketing

| Task | Priority | Status | Notes |
| --- | --- | --- | --- |
| Define your IT service niche | ⚡ Urgent | ✅ Done | Positioned as "Malaysia's AI-First IT Partner"; services consolidated into Foundation / Growth / AI Partner tiers. |
| Design company logo and select brand colours | High | ✅ Done | Navy #1E2D3D, Gold #C9A227, Silver #B8BEC8, Off-white #F8F9FB; Rajdhani Bold / Inter Light. |
| Build a professional website | High | ✅ Done | Live at dutaintegra.my — EN + Malay (ms/) versions maintained in sync. |
| Set up LinkedIn Company Page and optimize founder profile | High | ❓ Confirm | Status not confirmed in our records — flag if this still needs doing. |
| Set up Google Business Profile for local visibility | High | ❓ Confirm | Status not confirmed — worth doing for Cyberjaya-area SME discovery. |
| Create a company profile / pitch deck (PDF) | High | ⏳ Pending | Not yet produced — will matter for MDAG grant application and investor outreach (Cradle, MDEC). |
| Set up professional email (e.g. name@dutaintegra.my) | High | ⏳ Pending | Outstanding admin item — still open. |
| Register social media handles (LinkedIn, Facebook, Instagram) | Medium | ❓ Confirm | Status not confirmed in our records. |

🤝 PHASE 3 — Finding First Clients

| Task | Priority | Status | Notes |
| --- | --- | --- | --- |
| List 20 warm contacts to reach out to | ⚡ Urgent | ✅ Done | Effectively superseded — active client base already established. |
| Send personalized messages announcing the company | ⚡ Urgent | ✅ Done | Superseded by current focus: 3 personalised retainer-conversion emails drafted for Lapango, Eastelpro, AGMX. |
| Identify 10 target SME companies that may need IT services | High | 🔄 In Progress | Ongoing as part of pipeline-building beyond the current 3 clients. |
| Offer a free IT audit or discounted pilot to first 2–3 clients | High | ✅ Done | Lapango and Eastelpro on Foundation tier, AGMX on Growth (tentative) — original pilot cohort essentially in place. |
| Join PIKOM, MDEC, or local tech industry associations | High | ❓ Confirm | Status not confirmed — MDEC relevant for MDAG grant path too. |
| Attend at least 1 local tech/business networking event per month | Medium | ❓ Confirm | Status not confirmed. |
| Collect testimonials and case studies from first clients | Medium | ⏳ Pending | Not yet started — becomes important once retainers are signed, for grant/investor credibility. |
| List services on B2B platforms / directories | Medium | ❓ Confirm | Status not confirmed. |

👥 PHASE 4 — Building a Team

| Task | Priority | Status | Notes |
| --- | --- | --- | --- |
| Identify the 1–2 key roles needed most urgently | High | 🔄 In Progress | First tech hire planned around Month 6 of forecast horizon (base case). |
| Decide: hire full-time vs. freelancers/contractors | High | ⏳ Pending | Decision not yet finalised — tie to retainer MRR milestones. |
| Draft simple employment/freelance agreement template | High | ◻ Not Started | Not started — needed before first hire. |
| Post job openings (JobStreet, LinkedIn Jobs, referrals) | Medium | ◻ Not Started | Not yet — premature until hire timing/role is locked. |
| Set up basic HR policies (leave, conduct, hours) | Medium | ◻ Not Started | Not started. |
| Use a project management tool for team coordination | Medium | ❓ Confirm | Status not confirmed — worth locking in before first hire onboards. |

⚡ Real Next Actions (replaces "Month 1 Quick Wins")

1.  Get the PDPA Policy and Service Agreement + NDA through Malaysian legal review — this unblocks sending the 3 retainer proposals.

2.  Register LHDN tax number and set up professional email — both outstanding admin items with no dependency blocking them.

3.  Fill in per-client scope bullets and confirm Foundation/Growth monthly fees, then send the Lapango, Eastelpro, and AGMX outreach emails.

4.  Delete the duplicate Vercel project (shamelali-dutaintegraweb-main) to stop wasting build minutes.

5.  Once a retainer or two is signed, start collecting testimonials — needed for both the MDAG grant application and eventual investor conversations.