DUTA INTEGRA SOLUTIONS

Growth Roadmap — Becoming the Household IT Partner for Malaysian SMEs

Prepared: 13 September 2026  |  Internal strategy document — not for client distribution

# Why this roadmap

Duta Integra sells human-led retainers, not a self-serve outreach bot — so this isn't about copying Explee's funnel. It's about borrowing the two things Explee gets structurally right: a tight, repeatable outreach sequence, and a homepage built entirely from visible proof rather than claims. Everything below is scoped for a services business with three live client relationships (Lapango, Eastelpro, AGMX) and a small team, not a VC-funded SaaS.

# 1. Lead-generation playbook (adapted from Explee's 7-step flow)

| # | Explee step | DI equivalent | Action |
| --- | --- | --- | --- |
| 1 | Learns what you sell | Learn the prospect's stack | Pull a quick tech/ops snapshot of the target SME (site, socials, hiring posts, visible tools) before first contact. |
| 2 | Figures out who buys it | Score fit against the ICP | Build a rubric (revenue band, headcount, IT spend, PDPA exposure) to route prospects to the right tier. |
| 3 | Finds those exact people | Identify the real decision-maker | For Malaysian SMEs this is almost always the owner/MD directly — confirm before sending. |
| 4 | Writes each a personal email | Personalize every conversion email | Standing step for every new prospect, not a one-off — already proven with Lapango/Eastelpro/AGMX. |
| 5 | Handles replies, books meetings | Make the next step frictionless | Pre-built booking link + one-page “what to expect on the call” so replies convert same-day. |
| 6 | Learns what works, doubles down | Track what converts by client type | Tag which pain point / tier / channel worked so the next 10 targets get the highest-converting pitch. |
| 7 | Compounds via proof | Feed wins back into the site | Every signed retainer becomes a testimonial/case-study input — closes the loop into the site itself. |

# 2. Functionality roadmap

Phased by effort and dependency, not strict calendar time — move faster where capacity allows.

| Functionality | What it does | Effort | Owner | Why it matters |
| --- | --- | --- | --- | --- |
| PHASE A — 0-30 days: Trust foundation |  |  |  |  |
| Tier-recommendation quiz | 2-min self-assessment on site; recommends Foundation/Growth/AI Partner based on team size, IT spend, pain points. | Low (1-2 days, on Vercel) | Shamel + Claude | Matches the “we'll recommend the right tier, no pressure” promise already in the site copy; lowers friction before the proposal ask. |
| Case study template | One-page structured template (problem → what DI did → measurable result) applied to each signed retainer. | Low (template + 1 case study) | Shamel | Single highest-leverage credibility asset for Malaysian B2B buyers — direct input to grant/investor materials too. |
| Testimonial capture step | Standing ask built into the offboarding/monthly-review process for every client. | Low (process only) | Shamel | Currently zero client proof on the site; this is the pipeline that fixes it going forward. |
| PHASE B — 30-60 days: Proof & retention infrastructure |  |  |  |  |
| PDPA readiness tool | Free interactive checklist/scorecard (SSM, PDPA, MyInvois-readiness) as a lead magnet on the site. | Medium (1-2 weeks) | Shamel + dev | Turns DI's own compliance credibility into a funnel; matches the PDPA-policy work already in progress. |
| Client portal MVP | DutaConnect-powered dashboard: ticket status, SLA response times, monthly automated health report. | Medium-High (3-4 weeks) | Shamel + dev | Most Malaysian IT vendors don't offer this — cheap differentiator, increases retainer stickiness, justifies AI Partner pricing. |
| Monthly “what we did for you” digest | Automated email summarizing work completed for each retainer client that month. | Low-Medium (automation build) | Shamel + dev | Keeps DI visible between tickets; natural upsell moment into the next tier. |
| PHASE C — 60-90 days: Authority & visible proof |  |  |  |  |
| “Built by DI” live stats | Modest, honest live counters for DutaConnect/AGMX (automations run, uptime, compliance items handled). | Medium (needs product telemetry) | Shamel + dev | Same instinct as Explee's live counters, scaled honestly — makes the “AI-first” claim concrete. |
| MDEC / PIKOM membership | Formal association membership + badge on site and pitch materials. | Low (admin + fee) | Shamel | Enterprise buyers in Malaysia check for this before signing; also relevant to the MDAG grant path. |
| Recurring content series | Short LinkedIn/site posts built from real AGMX/DutaConnect learnings (“what we learned automating AGM compliance for an SME”). | Low, ongoing | Shamel | Builds household-name recognition in a B2B market this size through visible expertise, not ad spend. |
| PHASE D — 90+ days: Full self-serve funnel |  |  |  |  |
| Automation savings calculator | SME owner inputs team size/manual tasks → estimated hours/cost saved by tier. | Medium (2 weeks) | Shamel + dev | Turns an abstract AI pitch into a concrete number the owner can act on immediately. |
| Objection-handling FAQ | Site FAQ addressing data ownership, contract flexibility, AI reliability — the Malaysian SME version of Explee's compliance FAQ. | Low (copywriting) | Shamel | Removes friction before “Get a proposal” without needing a sales call to answer it. |

# 3. Immediate next actions

- Fix the footer phone number on both index.html and ms/index.html to +60 11-5403 4051, redeploy, purge Cloudflare cache.

- Draft the tier-recommendation quiz logic and 3-5 branching questions (Phase A, quick win).

- Apply the case study template to the first client that signs a retainer.

- Scope the PDPA readiness tool as a lead magnet alongside the in-progress PDPA Compliance Policy.

- Decide whether the client portal MVP rides on DutaConnect or is a standalone build — affects Phase B timeline.

- Confirm MDEC/PIKOM membership status and apply if not already a member.